## Slide 1: Weekly Productivity Update Month: May Week No: 3 Reporting Date: 05/25/2026 Presented By: Kevin Mensah

## Slide 2: Part 1.3: Weekly Planned vs Actual Analysis
Category | Application/Domain | Task/Activity Description | Planned/ Unplanned | Planned | Actual | Remarks
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Team Meetings | Planned | 1.00 | 1.00 | huddle
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Team Meetings | Planned | 1.00 | 1.00 | weekly meeting
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Team Meetings | Planned | 1.00 | 1.00 | weekly reporting
Others | Admin Work | Update of Productivity Log | Planned | 1.00 | 1.00 | Productivity Log Updating
Project | [SFA-Web] Expenses Revamp | Post-Go Live: Performance Monitoring | Planned | 9.00 | 8.00 | Support
Project | [SFA-Web] Expenses Revamp | Post-Go Live: System Enhancements | Planned | 0.00 | 6.00 | Blocking Disbursement and Condition Checking Fix for Verifier
Project | [SFA-App] Sales Return & Replace | Post-Go Live: Performance Monitoring | Planned | 9.00 | 5.00 | Support

## Slide 3: Part 1.3: Weekly Planned vs Actual Analysis
Category | Application/Domain | Task/Activity Description | Planned/ Unplanned | Planned | Actual | Time | Remarks
Project | [SFA-App] Sales Return & Replace | Testing: UAT | Planned | 0.00 | 5.00 |  | Issue Log Fixing
Major Enhancements | [SFA-Web] [Web Revamp] FSP Mapping | Design: Alignment Meeting | Planned | 1.00 | 1.00 |  | Solutioning for FSP Mapping
Major Enhancements | [SFA-Web] PO Attachment | Testing: System Testing | Planned | 3.00 | 0.00 |  | With Mobile???
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Analysis | Planned | 2.00 | 2.00 |  | Fuel Billing Support
Major Enhancements | [SFA-Web] [Web Revamp] FSP Mapping | Design: Alignment Meeting | Planned | 1.00 | 0.00 |  | Solutioning for FSP Mapping
Project | [SFA-App] Sales Return & Replace | Testing: System Testing | Planned | 1.00 | 1.00 |  | UAT Demo
Project | [SFA-App] Sales Return & Replace | Testing: System Testing | Planned | 0.00 | 1.50 |  | Internal Testing W/Mobile

## Slide 4: Part 1.3: Weekly Planned vs Actual Analysis
Category | Application/Domain | Task/Activity Description | Planned/ Unplanned | Planned | Actual | Remarks
Major Enhancements | [SFA-Web] [Web Revamp] Collection Receiving | Planning: Analysis | Planned | 15.00 | 5.00 | Review Process
Project | [SFA-App] OCR | Testing: Alignment Meeting | Planned | 0.00 | 0.50 | OCR Integration Testing
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Team Meetings | Planned | 0.00 | 3.00 | Rollout Meeting
 |  |  | Total: | 45.00 | 45.00 | 

## Slide 5: Part 1.3: Weekly Planned vs Actual Analysis
The total planned hours of 45 hours matched the total actual hours, resulting in a variance of 0 hours, which indicates that work was completed as expected. The Operations & Maintenance category had a significant amount of work, with an over-run of 3 hours in Team Meetings, which was not initially planned. This week's data suggests that the team was able to adapt to changing priorities, as evidenced by the unplanned work on System Enhancements for the SFA-Web Expenses Revamp project.

## Slide 6: Part 2.1: Project Progress Update
Project Name: | [SFA-Web] [Web Revamp] FSP Mapping | Planned Start Date: | 04/06/2026
Description: | Implementation Documentation & Test Case Creation for FSP Mapping | Planned Finish Date: | 05/31/2026
Planned Deliverables This Week | 
Implementation / Testing Implementation: Documentation — Technical Documentation Meeting Implementation: Documentation — Functional Documentation Meeting Testing: Test Case Creation — FSP Mapping test cases compared with SFA | Done

## Slide 7: Part 2.1: Project Progress Update
Project Name: | [SFA-Web] [Web Revamp] Customer Bank Accs | Planned Start Date: | 04/06/2026
Description: | MOP + merge | Planned Finish Date: | 05/31/2026
Planned Deliverables This Week | 
Environment Setup (To main merge) MOP Creation | Done

## Slide 8: Part 2.1: Project Progress Update
Project Name: | [SFA-Web] Expenses Revamp User Maintenance | Planned Start Date: | 04/06/2026
Description: | MOP + merge | Planned Finish Date: | 05/31/2026
Planned Deliverables This Week | 
UAT | Ongoing

## Slide 9: Part 2.2: Support Summary (Customer Requests) Part 2.3: Key Impact Delivered This Week Part 2.4: Risk/Escalation Needed
App/Domain | No Of Tickets | Critical | Major | Minor | Resolved | Pending
Expense Revamp | 3 | 1 | 1 | 1 | 1 | 2
Delivered FSP Mapping Implementation Documentation (technical + functional) and Test Case Creation
Produced Data Dictionary / RTM documentation across all owned modules that helps in traceability for future modules.
Meeting with Miss Eula for FSP mapping demo

## Slide 10: Part 2.2: Support Summary (Customer Requests) Part 2.3: Key Impact Delivered This Week Part 2.4: Risk/Escalation Needed
App/Domain | Ticket # | Severity | Request Date | Status | Resolved Date
Expense Revamp | 4354 | P1 | May 13 | Done | May 15
Delivered FSP Mapping Implementation Documentation (technical + functional) and Test Case Creation
Produced Data Dictionary / RTM documentation across all owned modules that helps in traceability for future modules.
Meeting with Miss Eula for FSP mapping demo

## Slide 11: Thank you!