## Slide 1: Weekly Productivity Update Month: May Week No: 1 Reporting Date: 05/25/2026 Presented By: Kevin Mensah

## Slide 2: Part 1.3: Weekly Planned vs Actual Analysis
Category | Application/Domain | Task/Activity Description | Planned/ Unplanned | Planned | Actual | Remarks
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Team Meetings | Planned | 1.00 | 1.00 | huddle
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Team Meetings | Planned | 1.00 | 1.00 | weekly meeting
Operations & Maintenance | Maintenance (Not Reflected in Service Desk) | Team Meetings | Planned | 1.00 | 1.00 | weekly reporting
Others | Admin Work | Update of Productivity Log | Planned | 1.00 | 1.00 | Productivity Log Updating
Project | [SFA-App] Sales Return & Replace | Post-Go Live: Alignment Meeting | Planned | 1.00 | 1.00 | 
Project | [SFA-App] Sales Return & Replace | Implementation: Coding | Planned | 20.00 | 13.00 | 
Project | [SFA-App] Sales Return & Replace | Implementation: Unit Testing | Planned | 8.00 | 6.00 | 

## Slide 3: Part 1.3: Weekly Planned vs Actual Analysis
Category | Application/Domain | Task/Activity Description | Planned/ Unplanned | Planned | Actual | Time | Remarks
Project | [SFA-App] Sales Return & Replace | Implementation: Integration | Planned | 3.00 | 2.00 |  | Preparation from Local to UAT
Project | [SFA-Web] Expenses Revamp | Testing: UAT | Planned | 3.00 | 1.00 |  | Support UAT
Major Enhancements | [SFA-Web] [Web Revamp] Collection Receiving | Implementation: Coding | Planned | 4.00 | 4.00 |  | 
Project | [SFA-Web] Expenses Revamp | Implementation: Alignment Meeting | Planned | 1.00 | 1.00 |  | Masterfiles Discussion
Major Enhancements | [SFA-Web] [Web Revamp] FSP Mapping | Implementation: Documentation | Planned | 1.00 | 0.00 |  | Documentation
Project | [SFA-Web] Expenses Revamp | Post-Go Live: Updates and Patches | Planned | 0.00 | 12.00 |  | 
Project | [SFA-App] Sales Return & Replace | Design: Alignment Meeting | Planned | 0.00 | 1.00 |  | WEB DEMO

## Slide 4: Part 1.3: Weekly Planned vs Actual Analysis
Category | Application/Domain | Task/Activity Description | Planned/ Unplanned | Planned | Actual | Remarks
Major Enhancements | [SFA-Web] [Web Revamp] Customer Bank Accs | Deployment: Environment Setup | Planned | 2.00 | 1.00 | Set up main branch and create merge req for Customer Bank Accounts
Major Enhancements | [SFA-Web] [Web Revamp] Customer Bank Accs | Implementation: Documentation | Planned | 1.00 | 2.00 | Customer Bank Accounts MOP Creation
Major Enhancements | [SFA-Web] [Web Revamp] MCP Report | Planning: Analysis | Planned | 9.00 | 9.00 | Code review in SFA
 |  |  | Total: | 45.00 | 45.00 | 

## Slide 5: Part 1.3: Weekly Planned vs Actual Analysis
The total planned hours of 45 hours matched the total actual hours, resulting in no variance, which means the workload was accurately forecasted. The [SFA-App] Sales Return & Replace project had the most work, with a notable under-run in the Implementation: Coding task, where 7 hours less were spent than planned. This week's key takeaway is that despite some tasks taking less time than expected, the overall workload was still completed as planned.

## Slide 6: Part 2.1: Project Progress Update
Project Name: | [SFA-Web] [Web Revamp] FSP Mapping | Planned Start Date: | 04/06/2026
Description: | Implementation Documentation & Test Case Creation for FSP Mapping | Planned Finish Date: | 05/31/2026
Planned Deliverables This Week | 
Implementation / Testing Implementation: Documentation — Technical Documentation Meeting Implementation: Documentation — Functional Documentation Meeting Testing: Test Case Creation — FSP Mapping test cases compared with SFA | Done

## Slide 7: Part 2.1: Project Progress Update
Project Name: | [SFA-Web] [Web Revamp] Customer Bank Accs | Planned Start Date: | 04/06/2026
Description: | MOP + merge | Planned Finish Date: | 05/31/2026
Planned Deliverables This Week | 
Environment Setup (To main merge) MOP Creation | Done

## Slide 8: Part 2.1: Project Progress Update
Project Name: | [SFA-Web] Expenses Revamp User Maintenance | Planned Start Date: | 04/06/2026
Description: | MOP + merge | Planned Finish Date: | 05/31/2026
Planned Deliverables This Week | 
UAT | Ongoing

## Slide 9: Part 2.2: Support Summary (Customer Requests) Part 2.3: Key Impact Delivered This Week Part 2.4: Risk/Escalation Needed
App/Domain | No Of Tickets | Critical | Major | Minor | Resolved | Pending
Expense Revamp | 3 | 1 | 1 | 1 | 1 | 2
Delivered FSP Mapping Implementation Documentation (technical + functional) and Test Case Creation
Produced Data Dictionary / RTM documentation across all owned modules that helps in traceability for future modules.
Meeting with Miss Eula for FSP mapping demo

## Slide 10: Part 2.2: Support Summary (Customer Requests) Part 2.3: Key Impact Delivered This Week Part 2.4: Risk/Escalation Needed
App/Domain | Ticket # | Severity | Request Date | Status | Resolved Date
Expense Revamp | 4354 | P1 | May 13 | Done | May 15
Delivered FSP Mapping Implementation Documentation (technical + functional) and Test Case Creation
Produced Data Dictionary / RTM documentation across all owned modules that helps in traceability for future modules.
Meeting with Miss Eula for FSP mapping demo

## Slide 11: Thank you!